## Dashboard
ProjectTrack Governance Dashboard
Metric | Value | [6 empty] | Domain | Requirements
Total requirements | 80 | [6 empty] | ARC | 7
P0 requirements | 63 | [6 empty] | UI | 14
Total gates | 17 | [6 empty] | LNK | 4
UI/UX approval gates | 10 | [6 empty] | SCH | 9
Open questions | 26 | [6 empty] | TRK | 4
Acceptance-test seeds | 135 | [6 empty] | RES | 10
[8 empty] | CAL | 2
Current control status | [7 empty] | MPR | 10
Item | Status | Blocking Gate | Owner | Evidence | Next Action | Due | Notes | REP | 8
Handoff package | SELF-CHECK PASS / INDEPENDENT PENDING | G-HANDOFF-00 | Validation Codex | scripts/validate_handoff.py | Issue formal independent verdict |  | Product code remains blocked until PASS | INT | 3
Architecture | APPROVED | G-ARCH-01 | User | governance/approvals/G-ARCH-01_2026-09-02.md | Preserve approved invariants |  | No later architectural drift without change decision | NFR | 6
UI information architecture | APPROVED | UI-00 | User | governance/approvals/UI-00_2026-09-02.md | Prepare P02 after G-HANDOFF-00 PASS |  | UI-01 remains mandatory | GOV | 3
Product code | BLOCKED | G-HANDOFF-00 | Implementation Codex | CODEX_NEXT_TASK.md | Validate package, then execute P02 only |  | Stop at UI-01
Codex cloud handoff | BLOCKED | Dedicated GitHub repository | User | Repository/environment | Connect dedicated private repository |  | No remote handoff confirmed

## Phase Gates
Gate ID | Phase | Type | Authority | Blocking | Status | Objective | Evidence Path | Approval Record | Notes
G-HANDOFF-00 | P00 | technical | Validation Codex | YES | PENDING | Prove the repository handoff is complete and internally consistent.
G-ARCH-01 | P01 | technical+human | User after validator eligibility | YES | APPROVED | Approve domain architecture, scheduling rules, data ownership and unresolved-decision register before product code. | governance/approvals/G-ARCH-01_2026-09-02.md | G-ARCH-01_2026-09-02.md | Explicit user approval recorded; independent G-HANDOFF-00 remains pending.
UI-00 | P01/P02 | ui_ux | User only | YES | APPROVED | Approve information architecture, command model, visual direction and All Projects concept before detailed frontend implementation. | governance/approvals/UI-00_2026-09-02.md | UI-00_2026-09-02.md | Explicit user approval recorded; UI-01 is the next frontend gate.
UI-01 | P02 | ui_ux | User only | YES | PENDING | Approve the executable desktop shell, navigation, tabs, panes and contextual command structure.
G-ENG-02 | P03 | technical | Validation Codex | YES | PENDING | Prove deterministic calendar, dependency, constraint and full-scheduler correctness.
UI-02 | P04 | ui_ux | User only | YES | PENDING | Approve Schedule View structure, density, hierarchy, compact view and visual fidelity.
UI-03 | P05 | ui_ux | User only | YES | PENDING | Approve direct-manipulation tools, graphical linking, feedback and undo behavior.
G-ENG-03 | P06 | technical | Validation Codex | YES | PENDING | Prove Scheduled/Revised/Actual transitions, baselines, summaries, CPM and persistence.
UI-04 | P07 | ui_ux | User only | YES | PENDING | Approve All Projects compact, selective expansion and expand-everything workflows.
G-ENG-04 | P08 | technical | Validation Codex | YES | PENDING | Prove resource, work, allocation, calendar and cost calculations.
UI-05 | P08 | ui_ux | User only | YES | PENDING | Approve Resource View and cross-project workload interaction.
UI-06 | P06 | ui_ux | User only | YES | PENDING | Approve visual language for Scheduled, Revised, Actual, progress, baseline, critical path and variance.
UI-07 | P09 | ui_ux | User only | YES | PENDING | Approve the wall-calendar view, stacking, labels and editing behavior.
UI-08 | P10 | ui_ux | User only | YES | PENDING | Approve layouts, reports, summary graphs, visual objects and print preview.
G-REL-01 | P11 | technical | Validation Codex | YES | PENDING | Prove supported import/export round trips and compatibility reporting.
UI-09 | P12 | ui_ux | User only | YES | PENDING | Approve the complete integrated desktop experience.
G-REL-02 | P12 | release | User after validator eligibility | YES | PENDING | Approve release candidate after regression, performance, resilience and recovery evidence.

## UI UX Gates
Gate | Objective | Must Demonstrate | Pass Authority | Validator Eligible | User Decision | Evidence Path | User Comments | Commit SHA | Date
UI-00 | Information architecture and visual direction | All Projects + individual tabs; Schedule/Resource/Calendar; dense original desktop command model; compact/expanded hierarchy; timeline and row scaling. | User only | NO | APPROVED | governance/approvals/UI-00_2026-09-02.md | APPROVE UI-00 — both gates approved; no conditions stated. | 4a773b4093f9db825a0651de4f436458030bad7d | 2026-09-02
UI-01 | Application shell and navigation | Tab workspace; view switching; contextual commands; shortcuts; panes; status; error/loading/empty states. | User only | NO | PENDING
UI-02 | Schedule View structure | Grid/timeline sync; hierarchy; compact view; summary bars; Show Level; density/row scaling; multiple bars; QuickLook; large fixture. | User only | NO | PENDING
UI-03 | Direct manipulation and tools | Arrow/Bar/Link/Revise/Percent/Text; Lock Tool; draw/move/resize/link; invalid feedback; keyboard; compound undo. | User only | NO | PENDING
UI-04 | All Projects master workspace | Project summary rows; selective expansion; nested expansion; Expand Everything; Active Now; one shared timeline. | User only | NO | PENDING
UI-05 | Resource View | Resource table; usage subrows; assignments; overload; calendars; cross-project usage; sync. | User only | NO | PENDING
UI-06 | Tracking/baseline visuals | Scheduled/Revised/Actual/Baseline; progress; critical path; datelines; variance; all key states. | User only | NO | PENDING
UI-07 | Calendar View | Continuous wall calendar; spanning bars; milestones; collision; inspection/editing; synchronization. | User only | NO | PENDING
UI-08 | Reporting and print | Layouts/filters/sorts/ranges/reports; summary graphs; visual objects; print preview; PDF. | User only | NO | PENDING
UI-09 | Final integrated experience | End-to-end All Projects-to-report journey, reopen/recovery and approved performance. | User only | NO | PENDING

## Feature Matrix
Requirement ID | Capability | Priority | Evidence | Understanding | Achievability | Target Phase | Target Gate | Implementation Status | Validation Status | User Approval | Main Gap | Closure Plan | Evidence Path | Owner | Validator
ARC-01 | Row separate from Bar | P0 | D/S/U | Confirmed | A | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Risk of UI flattening model | Schema invariants and N-bars-per-row tests |  | Implementation Codex | Validation Codex
ARC-02 | Multiple bars per row | P0 | D | Strongly supported | B | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Exact selection and display not yet shown | Obtain multi-bar screenshot/workflow |  | Implementation Codex | Validation Codex
ARC-03 | Scheduled/Revised/Actual | P0 | S/D | Confirmed | B | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | State transitions need rules | Formal transition table |  | Implementation Codex | Validation Codex
ARC-04 | Ten baselines | P0 | D | Strongly supported | A | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Visual comparison not shown | Baseline-view evidence and tests |  | Implementation Codex | Validation Codex
ARC-05 | Stable row number and Bar ID | P0 | S | Confirmed | A | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Renumbering rules open | Separate immutable IDs and display numbers |  | Implementation Codex | Validation Codex
UI-01 | Spreadsheet + timeline | P0 | S | Confirmed | A/B | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Many edge cases | Grid and timeline interaction spec |  | Implementation Codex | Validation Codex
UI-02 | Global Show Level | P0 | S/U | Confirmed | A | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Persistence rules | Outline-state model |  | Implementation Codex | Validation Codex
UI-03 | Compact summary view | P0 | S/U | Confirmed | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Summary mathematics | Golden summary schedules |  | Implementation Codex | Validation Codex
UI-04 | Continuous timeline density | P0 | U/S | Confirmed | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Anchor/zoom behaviour | Coordinate-transform tests |  | Implementation Codex | Validation Codex
UI-05 | Global and per-row height | P0 | U/S | Confirmed | B | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Autofit precedence | Canonical row geometry model |  | Implementation Codex | Validation Codex
UI-06 | Tool-state machine | P0 | S/D | Confirmed | A/B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Input conflicts | Central ToolController |  | Implementation Codex | Validation Codex
UI-07 | Lock Tool | P0 | S | Confirmed | A | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | One-shot vs repeat rules | Explicit state transitions |  | Implementation Codex | Validation Codex
UI-08 | Bar styles/components | P0 | S/D | Confirmed | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Full editor not yet shown | Finite primitive style engine |  | Implementation Codex | Validation Codex
UI-09 | Floating report objects | P0 | S/D | Confirmed | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Pointer/Object semantics | Observe dialogs; separate overlay layer |  | Implementation Codex | Validation Codex
UI-10 | QuickLook | P0 | S | Confirmed | A | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Configurability | Hover-card field definition |  | Implementation Codex | Validation Codex
LNK-01 | Graphical Link tool | P0 | S/U | Confirmed | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Exact endpoint gesture | Controlled linking experiment |  | Implementation Codex | Validation Codex
LNK-02 | FS/SS/FF/SF | P0 | D | Strongly supported | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Editing dialog unseen | Links-tab screenshot/test |  | Implementation Codex | Validation Codex
LNK-03 | Lag/lead | P0 | D | Strongly supported | B | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | Unit rules | Dependency schema/tests |  | Implementation Codex | Validation Codex
LNK-04 | Cycle rejection | P0 | P/conventional | Required | A | P05 Direct manipulation | UI-03 | NOT STARTED | NOT VALIDATED | PENDING | UI explanation | Graph validation + highlight cycle |  | Implementation Codex | Validation Codex
SCH-01 | Work calendars | P0 | S/D | Confirmed | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Precedence rules | Independent calendar engine |  | Implementation Codex | Validation Codex
SCH-02 | Time-of-day scheduling | P0 | S | Confirmed | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | DST/timezone | Timestamp policy |  | Implementation Codex | Validation Codex
SCH-03 | Fractional duration | P0 | S | Confirmed | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | precision/rounding | Normalized time units |  | Implementation Codex | Validation Codex
SCH-04 | Constraints | P0 | S/D | Confirmed | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | conflict precedence | Scheduling rules document |  | Implementation Codex | Validation Codex
SCH-05 | Fixed Duration | P0 | S | Confirmed | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | interaction with work/resources | Lock-variable matrix |  | Implementation Codex | Validation Codex
SCH-06 | Ignore Resource Calendars | P0 | S | Confirmed | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | inheritance | Calendar-precedence matrix |  | Implementation Codex | Validation Codex
SCH-07 | Critical path and float | P0 | D/S menu | Strongly supported | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | calendars/constraints complexity | CPM conformance tests |  | Implementation Codex | Validation Codex
SCH-08 | Bar Priority | P0 | S/D | Confirmed field | B | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | exact semantics | Define ProjectTrack rule if undocumented |  | Implementation Codex | Validation Codex
SCH-09 | Incremental scheduler | P0 | P | Required | B/C | P03 Calendar and scheduler core | G-ENG-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | correctness/performance | Full solver first, dirty graph later |  | Implementation Codex | Validation Codex
TRK-01 | Revise tool | P0 | S | Confirmed | B | P06 Tracking and baselines | UI-06 | NOT STARTED | NOT VALIDATED | PENDING | visual and downstream rules | Controlled experiment |  | Implementation Codex | Validation Codex
TRK-02 | Percent tool / Actual | P0 | S | Confirmed | B | P06 Tracking and baselines | UI-06 | NOT STARTED | NOT VALIDATED | PENDING | percent-to-actual maths | Tracking rules specification |  | Implementation Codex | Validation Codex
TRK-03 | Reset Revised/Actual | P0 | S | Confirmed | B | P06 Tracking and baselines | UI-06 | NOT STARTED | NOT VALIDATED | PENDING | cascade semantics | State-transition tests |  | Implementation Codex | Validation Codex
TRK-04 | Save/Clear Baseline | P0 | S | Confirmed | A/B | P06 Tracking and baselines | UI-06 | NOT STARTED | NOT VALIDATED | PENDING | multi-baseline UX | Baseline selector and tests |  | Implementation Codex | Validation Codex
RES-01 | Resource master table | P0 | S | Confirmed | A | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | Low | Implement directly |  | Implementation Codex | Validation Codex
RES-02 | Detailed resource record | P0 | S | Confirmed | A | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | Field optionality | Normalized contact/profile model |  | Implementation Codex | Validation Codex
RES-03 | Resource calendar | P0 | S | Confirmed | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | inheritance | Same calendar engine |  | Implementation Codex | Validation Codex
RES-04 | Percent Work Usage | P0 | S menu/D | Partially understood | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | rendering/editing unseen | Expanded Resource View capture |  | Implementation Codex | Validation Codex
RES-05 | Work Usage | P0 | S menu/D | Partially understood | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | time-bucket semantics | Resource fixture and capture |  | Implementation Codex | Validation Codex
RES-06 | Assignments subrow | P0 | S menu/D | Partially understood | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | direct editing unseen | Assignment workflow capture |  | Implementation Codex | Validation Codex
RES-07 | Contours | P1 | D/V | Strongly supported | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | exact curves | Define normalized functions |  | Implementation Codex | Validation Codex
RES-08 | Spot allocation | P1 | D | Strongly supported | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | precedence with contours | Deterministic allocation rules |  | Implementation Codex | Validation Codex
RES-09 | Overtime | P1 | S/D | Confirmed fields; model partial | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | threshold rules | Resource overtime policy |  | Implementation Codex | Validation Codex
RES-10 | Effort-driven schedule | P1 | D/V | Strongly supported | B | P08 Resource and cost engine | UI-05 | NOT STARTED | NOT VALIDATED | PENDING | variable locking | Formal equations |  | Implementation Codex | Validation Codex
CAL-01 | Calendar wall view | P0 | S | Confirmed | B | P09 Calendar View | UI-07 | NOT STARTED | NOT VALIDATED | PENDING | direct manipulation unseen | Calendar drag/edit capture |  | Implementation Codex | Validation Codex
CAL-02 | Calendar exceptions/shifts | P0 | S | Confirmed | B | P09 Calendar View | UI-07 | NOT STARTED | NOT VALIDATED | PENDING | inheritance precedence | Calendar tests |  | Implementation Codex | Validation Codex
MPR-01 | File consolidation | P0 | S/D | Confirmed | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | update ownership | Consolidation rules |  | Implementation Codex | Validation Codex
MPR-02 | Common finish projects | P0 | S | Confirmed option | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | exact alignment | Controlled consolidation test |  | Implementation Codex | Validation Codex
MPR-03 | Separate finish projects | P0 | S | Confirmed option | A/B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | Low | Preserve independent timelines |  | Implementation Codex | Validation Codex
MPR-04 | Native All Projects tab | P0 | U | Confirmed requirement | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | workspace architecture | Build into domain from Phase 0 |  | Implementation Codex | Validation Codex
MPR-05 | Project collapses to one row | P0 | U | Confirmed | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | roll-up calculations | Project summary engine |  | Implementation Codex | Validation Codex
MPR-06 | Expand all projects/all rows | P0 | U | Confirmed | A/B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | performance | Virtualized master tree |  | Implementation Codex | Validation Codex
MPR-07 | Combined sequential steps | P0 | U | Confirmed concept | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | exact ordering | Define sort/group semantics |  | Implementation Codex | Validation Codex
MPR-08 | Cross-project grouping | P0 | P | Proposed | A/B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | User approval | Keep optional |  | Implementation Codex | Validation Codex
REP-01 | Layouts | P1 | S/D | Confirmed | A/B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | state-versioning | Versioned ViewState |  | Implementation Codex | Validation Codex
REP-02 | Filters | P1 | S/D | Confirmed | B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | multiple-bar semantics | Filter AST |  | Implementation Codex | Validation Codex
REP-03 | Sorts | P1 | S/D | Confirmed | A/B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | hierarchy behaviour | explicit mode |  | Implementation Codex | Validation Codex
REP-04 | Timeline Ranges | P1 | S/D | Confirmed | A | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | Low | persist definitions |  | Implementation Codex | Validation Codex
REP-05 | Reports as saved view states | P1 | D | Strongly supported | B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | breadth of captured state | reusable ViewStateSnapshot |  | Implementation Codex | Validation Codex
REP-06 | FastSteps | P1 | S/D | Confirmed | A/B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | exact commands | safe command vocabulary |  | Implementation Codex | Validation Codex
REP-07 | Summary Graphs | P1 | S/D | Confirmed | B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | aggregation semantics | graph engine after core |  | Implementation Codex | Validation Codex
REP-08 | Header/Footer/Page Break | P1 | S | Confirmed | B | P10 Reporting and print | UI-08 | NOT STARTED | NOT VALIDATED | PENDING | pagination | print-layout engine |  | Implementation Codex | Validation Codex
INT-01 | CSV/XLSX/XML/ICS/HTML/PDF | P1 | D/P | Required | B | P11 Interoperability | G-REL-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | mapping loss | compatibility report |  | Implementation Codex | Validation Codex
INT-02 | Native MPP | P1 | D | Conditional | C/D | P11 Interoperability | G-REL-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | proprietary format/library | XML fallback |  | Implementation Codex | Validation Codex
INT-03 | Vector clipboard | P1 | D/P | Conditional | C | P11 Interoperability | G-REL-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Windows/Tauri integration | PNG → SVG → EMF stages |  | Implementation Codex | Validation Codex
NFR-01 | 10k-row performance | P0 | P | Required | B | P12 Release hardening | G-REL-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | actual latency | automated benchmarks |  | Implementation Codex | Validation Codex
NFR-02 | 100-step undo | P0 | P | Required | B | P12 Release hardening | G-REL-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | large commands | reversible domain commands |  | Implementation Codex | Validation Codex
NFR-03 | Autosave/recovery | P0 | P/D | Required | A/B | P12 Release hardening | G-REL-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | corruption | atomic snapshots/WAL |  | Implementation Codex | Validation Codex
NFR-04 | Background jobs | P0 | D/P | Required | B | P12 Release hardening | G-REL-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | safe cancellation | staging and rollback |  | Implementation Codex | Validation Codex
NFR-05 | Exact FastTrack visual clone | P2 | U/Policy | Not targeted | D by design | P12 Release hardening | G-REL-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Copyright and unnecessary parity | Original UI, workflow equivalence |  | Implementation Codex | Validation Codex
NFR-06 | Exact undocumented FastTrack semantics | P2 | Methodology | Not promiseable | D | P12 Release hardening | G-REL-02 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | unavailable evidence | compatibility ledger |  | Implementation Codex | Validation Codex
ARC-06 | Workspace contains native project nodes, not only file references | P0 | U/S | Confirmed | B | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Risk of bolting portfolio on late | Model Workspace and Project from Phase 0 |  | Implementation Codex | Validation Codex
ARC-07 | Derived summary nodes at project, phase and activity-group levels | P0 | U/S | Confirmed | B | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Exact roll-up mathematics | Formal summary equations and golden fixtures |  | Implementation Codex | Validation Codex
UI-11 | Canonical row height shared by grid and timeline | P0 | U/S | Confirmed | B | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Variable wrapped rows can desynchronise | Single geometry service and visual tests |  | Implementation Codex | Validation Codex
UI-12 | Direct proportional timeline-header scaling | P0 | U/S | Confirmed | B | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Physical zoom can be confused with date range | Separate range, units and pixels-per-unit state |  | Implementation Codex | Validation Codex
UI-13 | Global and local Expand/Collapse and Show Level controls | P0 | U/S | Confirmed | A/B | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Outline state persistence | Tree projection tests at project and row level |  | Implementation Codex | Validation Codex
UI-14 | All Projects and individual project tabs in one workspace | P0 | U | Confirmed | B | P04 Schedule View structure | UI-02 | NOT STARTED | NOT VALIDATED | PENDING | Tab and projection ownership | Workspace shell approved at UI-00/UI-01 |  | Implementation Codex | Validation Codex
MPR-09 | See current work across every project in one window | P0 | U | Confirmed | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | Definition of active work and roll-up | Status-date rules and Active Now fixture |  | Implementation Codex | Validation Codex
MPR-10 | Expand every project and every step into one continuous scrollable sequence | P0 | U | Confirmed | B | P07 All Projects workspace | UI-04 | NOT STARTED | NOT VALIDATED | PENDING | Scale and performance | Virtualised master tree benchmark |  | Implementation Codex | Validation Codex
GOV-01 | Human approval required at each front-end UI/UX gate | P0 | U | Confirmed | A | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Agent may continue without approval | Hard stop and signed approval record |  | Implementation Codex | Validation Codex
GOV-02 | Independent validation task separate from implementation task | P0 | U | Confirmed | A | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Self-validation bias | Separate validation prompt and reports |  | Implementation Codex | Validation Codex
GOV-03 | No phase advances without evidence-backed checkpoint | P0 | U | Confirmed | A | P01 Architecture and governance | G-ARCH-01 | NOT STARTED | NOT VALIDATED | NOT REQUIRED | Status drift | Checkpoint record linked to commit SHA |  | Implementation Codex | Validation Codex

## Validation Matrix
Layer | Focus | Mandatory Checks | Pass Threshold | Owner | Status | Evidence Path | Defects | Next Action
L0 | Package/document integrity | Required files/images; unique IDs; valid JSON/CSV; no contradictory active instructions | 100% | Validation Codex | PENDING
L1 | Static architecture | Row/Bar split; state separation; canonical ownership; domain/view separation; full solver first | No invariant violation | Validation Codex | PENDING
L2 | Deterministic unit correctness | Calendar, dependencies, constraints, summaries, tracking, CPM, resource/cost, persistence | 100% required tests pass | Validation Codex | PENDING
L3 | Integration | Grid↔timeline; edits↔scheduler; resources↔schedule; project↔master; save/reopen; undo | No S0/S1 | Validation Codex | PENDING
L4 | UI interaction/visual | E2E, visual diff, keyboard/focus, resizing, collapse/expand, user-gate evidence | Eligible + user approval | Validation Codex + User | PENDING
L5 | Performance/resilience | Large fixtures, latency, memory, recovery, cancellation, rollback | Published phase threshold | Validation Codex | PENDING
L6 | Interoperability | Round trips, compatibility reports, malformed input, PDF/clipboard | Declared preservation met | Validation Codex | PENDING

## Open Questions
ID | Question | Impact | Decision Gate | Evidence/Action Required | Status | Decision | Owner | Due
Q-001 | What exact pointer gesture selects FS/SS/FF/SF during graphical linking? | Core interaction and dependency semantics | UI-03 | Record a controlled link-creation experiment for every endpoint combination. | OPEN
Q-002 | How is lag/lead entered and which unit/calendar governs it? | Scheduler correctness | G-ENG-02 | Capture Links tab/editor and run lag/lead experiments. | OPEN
Q-003 | What happens when a summary bar is moved or resized? | Roll-up and edit semantics | G-ARCH-01 | Controlled parent-summary experiment. | OPEN
Q-004 | Can parent Start/Finish/Duration cells be edited, and how do descendants respond? | Hierarchy scheduling | G-ARCH-01 | Controlled parent-cell experiment. | OPEN
Q-005 | How exactly is summary Duration calculated when child calendars differ? | Summary mathematics | G-ENG-03 | Golden schedules with mixed calendars. | OPEN
Q-006 | What is the weighting basis for summary and project percent complete? | Portfolio status | G-ENG-03 | Define and approve work/duration/manual weighting rules. | OPEN
Q-007 | How are Scheduled, Revised, Actual and baselines placed visually? | Tracking UX | UI-06 | Capture source examples or approve original ProjectTrack visual language. | OPEN
Q-008 | Does Reset Revised also clear Actual and percent complete? | State transition correctness | G-ENG-03 | Controlled reset experiment and transition table. | OPEN
Q-009 | How does the Percent tool derive Actual dates at partial completion? | Tracking mathematics | G-ENG-03 | Controlled 25/50/100 percent experiments. | OPEN
Q-010 | What are the expanded Resource View rows for Percent Work Usage, Work Usage and Assignments? | Resource UX and data model | UI-05 | Capture expanded resource view. | OPEN
Q-011 | What fields and controls exist in the assignment editor? | Resource engine | G-ENG-04 | Capture Assignments tab/dialog. | OPEN
Q-012 | What exact normalized curves define each work contour? | Resource allocation | G-ENG-04 | Document source curves or approve ProjectTrack-owned curves. | OPEN
Q-013 | What precedence do spot allocations have over contour-distributed work? | Resource allocation | G-ENG-04 | Controlled assignment fixture. | OPEN
Q-014 | How is overtime thresholded and distributed? | Cost correctness | G-ENG-04 | Formal overtime policy and fixtures. | OPEN
Q-015 | What is the exact variable-locking matrix for Fixed Duration and effort-driven tasks? | Scheduler-resource coupling | G-ENG-04 | Before/after resource experiments. | OPEN
Q-016 | Can activities be dragged and revised directly in Calendar View? | Calendar UX | UI-07 | Controlled calendar drag experiment. | OPEN
Q-017 | How are overlapping bars stacked in Calendar View? | Calendar readability | UI-07 | Dense collision fixture. | OPEN
Q-018 | Is a consolidated master directly editable or refreshed from child files? | Multi-project ownership | G-ARCH-01 | Define ProjectTrack canonical ownership before implementation. | OPEN
Q-019 | How are conflicts handled when a child project and master projection both change? | Data integrity | G-ARCH-01 | Choose source-of-truth and conflict policy. | OPEN
Q-020 | Can cross-project dependencies be created? | Portfolio scheduler | G-ARCH-01 | User decision plus scheduler impact analysis. | OPEN
Q-021 | Are resources global, project-local, or both, and how are duplicates matched? | Cross-project workload | G-ARCH-01 | Approve resource identity strategy. | OPEN
Q-022 | What does common-finish consolidation do mathematically? | Consolidation parity | G-ENG-03 | Controlled two-project consolidation experiment. | OPEN
Q-023 | Which alternative master groupings beyond By Project are required for V1? | Scope and UX | UI-00 | User selects among workstream/resource/department/status/chronological. | OPEN
Q-024 | What is the exact FastSteps command vocabulary and rollback behavior? | Automation | UI-08 | Capture Define dialog or approve ProjectTrack safe command list. | OPEN
Q-025 | What exact state is retained by Layouts, Reports, Filters, Sorts and Ranges? | View persistence | UI-08 | Capture definition dialogs and persistence tests. | OPEN
Q-026 | Which MPP library, if any, is reliable and legally suitable? | Interoperability | G-REL-01 | Technical/library assessment; XML fallback remains mandatory. | OPEN

## Test Catalog
Test ID | Category | Scenario | Action | Expected Result | Status | Evidence | Defect ID | Commit SHA
ARC-001 | ARC | Row with zero bars | Create a row with no bars, save and reopen | Row identity and row-level data persist without a synthetic task. | NOT RUN
ARC-002 | ARC | Row with multiple bars | Create three bars in one row and edit one | Only the selected bar state changes; row-level data remains shared. | NOT RUN
ARC-003 | ARC | Stable identities | Collapse, sort, filter and reopen | UUIDs, stable row numbers and visible bar IDs remain stable. | NOT RUN
ARC-004 | ARC | Project as tree node | Create three projects and expand one | The project is a native expandable node, not duplicated data. | NOT RUN
ARC-005 | ARC | Derived summary node | Change a descendant start/finish | Project/phase/activity summaries update without becoming editable source bars. | NOT RUN
CAL-001 | CAL | Typical weekday | Add 8 working hours Monday 09:00 | Finish is Monday 17:00 using split-shift rules. | NOT RUN
CAL-002 | CAL | Split shift | Start Monday 11:00 with 4h duration | Work skips lunch and finishes at 16:00. | NOT RUN
CAL-003 | CAL | Weekend skip | Start Friday 16:00 with 2h duration | Finish is Monday 10:00. | NOT RUN
CAL-004 | CAL | Holiday exception | Mark Monday non-working | Successor and finish dates move to next valid work period. | NOT RUN
CAL-005 | CAL | Working exception | Mark Saturday working | Calendar arithmetic includes Saturday shift. | NOT RUN
CAL-006 | CAL | Base calendar inheritance | Override one date in derived calendar | Only derived calendar changes and inheritance remains intact. | NOT RUN
CAL-007 | CAL | Resource exception | Resource unavailable on a task workday | Bar reschedules unless Ignore Resource Calendars is true. | NOT RUN
CAL-008 | CAL | Fractional day | Schedule 0.06 day with 8h base day | Duration normalizes consistently and round-trips without drift. | NOT RUN
CAL-009 | CAL | Timestamp precision | Schedule a task starting 13:30 | Date and time remain exact through save/reopen. | NOT RUN
CAL-010 | CAL | DST/timezone policy | Open project across DST boundary | Published ProjectTrack timezone policy is applied deterministically. | NOT RUN
DEP-001 | DEP | FS link | Link A finish to B start | B starts at first valid working instant after A finish. | NOT RUN
DEP-002 | DEP | SS link | Link A start to B start | B start follows A start plus lag. | NOT RUN
DEP-003 | DEP | FF link | Link A finish to B finish | B finish follows A finish plus lag. | NOT RUN
DEP-004 | DEP | SF link | Link A start to B finish | B finish follows A start plus lag. | NOT RUN
DEP-005 | DEP | Positive lag | Set FS +2 working days | Successor moves by two working days. | NOT RUN
DEP-006 | DEP | Negative lag | Set FS -1 working day | Successor overlaps predecessor by one working day. | NOT RUN
DEP-007 | DEP | Multiple predecessors | Attach three predecessors | Successor honors the controlling predecessor. | NOT RUN
DEP-008 | DEP | Multiple successors | Move one predecessor | All affected successors update. | NOT RUN
DEP-009 | DEP | Cycle rejection | Attempt A→B→C→A | Cycle is rejected, explained and no partial link remains. | NOT RUN
DEP-010 | DEP | Graphical link transaction | Create link by pointer and undo | One undo removes link and restores all downstream dates. | NOT RUN
DEP-011 | DEP | Delete link | Delete a controlling link | Affected Revised dates recalculate under remaining rules. | NOT RUN
DEP-012 | DEP | Link persistence | Save/reopen linked project | Endpoint IDs, type, lag and route semantics persist. | NOT RUN
CON-001 | CON | ASAP | Create unconstrained task | Task anchors at earliest allowed date. | NOT RUN
CON-002 | CON | ALAP | Create ALAP task | Task anchors at latest allowed date from project finish context. | NOT RUN
CON-003 | CON | SNET | Set Start No Earlier Than | Task never starts before constraint. | NOT RUN
CON-004 | CON | SNLT | Set Start No Later Than | Conflict is surfaced when dependencies violate constraint. | NOT RUN
CON-005 | CON | FNET | Set Finish No Earlier Than | Finish honors constraint. | NOT RUN
CON-006 | CON | FNLT | Set Finish No Later Than | Conflict is surfaced when impossible. | NOT RUN
CON-007 | CON | MSO | Set Must Start On | Start is fixed and conflict is explained. | NOT RUN
CON-008 | CON | MFO | Set Must Finish On | Finish is fixed and conflict is explained. | NOT RUN
CON-009 | CON | Constraint vs dependency | Apply conflicting rules | Deterministic precedence and visible conflict are produced. | NOT RUN
TRK-001 | TRK | Scheduled/Revised separation | Revise an existing bar | Scheduled remains unchanged; Revised changes. | NOT RUN
TRK-002 | TRK | Reset Revised | Revise then reset | Revised returns exactly to scheduled per approved transition rules. | NOT RUN
TRK-003 | TRK | Partial progress | Set 50 percent complete | Actual/progress representation follows approved rules. | NOT RUN
TRK-004 | TRK | Complete progress | Set 100 percent complete | Actual finish is populated and remaining work is zero. | NOT RUN
TRK-005 | TRK | Reset Actual | Enter actuals then reset | Actual fields and percent follow approved reset rules. | NOT RUN
TRK-006 | TRK | Status date | Move status date | Late/active classification updates without altering history. | NOT RUN
TRK-007 | TRK | Baseline save | Save baseline 1 | All supported baseline fields snapshot atomically. | NOT RUN
TRK-008 | TRK | Multiple baselines | Save baselines 1, 2 and 10 | Active baseline switches without data loss. | NOT RUN
TRK-009 | TRK | Clear baseline | Clear baseline 2 | Only baseline 2 is removed. | NOT RUN
TRK-010 | TRK | Variance | Revise after baseline | Start/finish/duration/work/cost variances compute correctly. | NOT RUN
TRK-011 | TRK | Tracking persistence | Save/reopen | Scheduled/Revised/Actual/baselines persist exactly. | NOT RUN
SUM-001 | SUM | Earliest/latest roll-up | Change first and last child dates | Summary start and finish update. | NOT RUN
SUM-002 | SUM | Progress roll-up | Change child progress | Summary percent follows approved weighting. | NOT RUN
SUM-003 | SUM | Cost roll-up | Change descendant costs | Summary cost equals qualifying descendant total. | NOT RUN
SUM-004 | SUM | Work roll-up | Change descendant work | Summary work equals qualifying descendant total. | NOT RUN
SUM-005 | SUM | Active count | Set status date inside child bars | Summary active count is correct. | NOT RUN
SUM-006 | SUM | Late count | Delay two descendants | Summary late count is correct. | NOT RUN
SUM-007 | SUM | Collapse/expand | Collapse and re-expand branch | Stable row numbers and prior expansion state remain intact. | NOT RUN
SUM-008 | SUM | Show Level | Set levels 1, 2, 3 and All | Visible tree matches requested outline depth. | NOT RUN
SUM-009 | SUM | Mixed calendars | Use different child calendars | Summary duration follows approved calendar rule. | NOT RUN
SUM-010 | SUM | Project roll-up | Collapse project to one row | Project summary bar/metrics accurately represent descendants. | NOT RUN
CPM-001 | CPM | Simple critical chain | Build linear dependency chain | All chain bars have zero total float. | NOT RUN
CPM-002 | CPM | Parallel paths | Build short and long paths | Only controlling longest path is critical. | NOT RUN
CPM-003 | CPM | Free float | Add gap before successor | Free float is calculated correctly. | NOT RUN
CPM-004 | CPM | Constraint impact | Add controlling constraint | Critical path and float update deterministically. | NOT RUN
CPM-005 | CPM | Mixed calendars | Use path-specific calendars | CPM uses calendar-aware arithmetic. | NOT RUN
CPM-006 | CPM | Priority tie | Create equal path candidates | Approved bar-priority rule selects deterministically. | NOT RUN
CPM-007 | CPM | Critical threshold | Set near-zero threshold | Critical display follows threshold. | NOT RUN
UI-001 | UI | Grid/timeline vertical sync | Scroll variable-height rows | Grid and timeline remain pixel-aligned. | NOT RUN
UI-002 | UI | Timeline density | Drag date-header spacing to 2x | All geometry scales 2x; schedule dates remain unchanged. | NOT RUN
UI-003 | UI | Global row scale | Increase row scale | All rows scale proportionally and bar centers remain aligned. | NOT RUN
UI-004 | UI | Per-row resize | Resize one row | Only that row changes; wrapped text and timeline match. | NOT RUN
UI-005 | UI | Autofit | Run row/column/view autofit | Content becomes readable without schedule mutation. | NOT RUN
UI-006 | UI | Draw bar | Use Bar tool to drag on row | Correct timestamps and style are created. | NOT RUN
UI-007 | UI | Move bar | Use Arrow tool to drag | Correct state changes and dependent preview is clear. | NOT RUN
UI-008 | UI | Resize bar | Drag left and right edges | Start/finish/duration update according to handle. | NOT RUN
UI-009 | UI | Lock tool | Lock Bar then create three bars | Tool remains active until unlocked. | NOT RUN
UI-010 | UI | QuickLook | Hover a bar | Approved fields display without selection change. | NOT RUN
UI-011 | UI | Keyboard navigation | Use Tab, Shift+Tab and shortcuts | Focus order and commands are predictable. | NOT RUN
UI-012 | UI | Invalid target feedback | Drag link to invalid target | Target is rejected with clear visual explanation. | NOT RUN
UI-013 | UI | Undo compound edit | Move predecessor with successors | One undo restores entire transaction. | NOT RUN
UI-014 | UI | View-state persistence | Save layout and reopen | Density, columns, rows, outline and toggles restore. | NOT RUN
MPR-001 | MPR | Projects only | Open All Projects compact mode | Every project is one meaningful summary row. | NOT RUN
MPR-002 | MPR | Selective expansion | Expand one project | Other projects remain collapsed. | NOT RUN
MPR-003 | MPR | Nested expansion | Expand project, phase and activity | Hierarchy drills down in same window. | NOT RUN
MPR-004 | MPR | Expand everything | Expand all projects and rows | One continuous virtualized sequence is produced. | NOT RUN
MPR-005 | MPR | Collapse everything | Collapse all | Returns to project-only rows without identity changes. | NOT RUN
MPR-006 | MPR | Shared timeline | Display projects with different dates | All align correctly on one timeline. | NOT RUN
MPR-007 | MPR | Current work | Apply Active Now view | Active activities across all projects are visible in context. | NOT RUN
MPR-008 | MPR | Separate finishes | Use independent-finish mode | Each project retains its own finish. | NOT RUN
MPR-009 | MPR | Common finish | Use common-finish mode | Approved alignment semantics are applied. | NOT RUN
MPR-010 | MPR | Missing child source | Remove referenced project file | Master reports missing source without data corruption. | NOT RUN
MPR-011 | MPR | Refresh | Change child project then refresh | Master updates according to ownership policy. | NOT RUN
MPR-012 | MPR | Duplicate resource identity | Consolidate same-named resources | Approved matching policy avoids accidental merging. | NOT RUN
RES-001 | RES | Resource record | Create people/equipment/material records | Typed profile fields persist. | NOT RUN
RES-002 | RES | Assignment units | Assign resource at 50 percent | Usage and work buckets reflect 50 percent capacity. | NOT RUN
RES-003 | RES | Over-allocation | Assign 11h into 8h capacity | Overload is detected and contributing bars are shown. | NOT RUN
RES-004 | RES | Resource calendar | Add resource exception | Affected schedule/use updates per rule. | NOT RUN
RES-005 | RES | Ignore resource calendar | Toggle flag | Task switches between resource-constrained and task/project calendar. | NOT RUN
RES-006 | RES | Fixed duration | Add second resource to fixed-duration task | Duration stays fixed and work/units follow approved lock matrix. | NOT RUN
RES-007 | RES | Effort driven | Double equivalent resources | Duration changes according to effort-driven rule. | NOT RUN
RES-008 | RES | Flat contour | Distribute work | Work is uniform across eligible buckets. | NOT RUN
RES-009 | RES | Early peak contour | Distribute work | Approved curve weights earlier buckets. | NOT RUN
RES-010 | RES | Spot allocation | Override one day | Manual bucket overrides contour and total reconciles. | NOT RUN
RES-011 | RES | Overtime | Exceed regular capacity | Regular and overtime work/cost separate correctly. | NOT RUN
RES-012 | RES | Rate override | Override assignment rate | Only that assignment cost uses override. | NOT RUN
RES-013 | RES | Per-use cost | Assign resource | Per-use cost is applied exactly once per policy. | NOT RUN
RES-014 | RES | Cross-project workload | Assign resource in three projects | Global Resource View aggregates all projects. | NOT RUN
PERSIST-001 | PERSIST | Atomic save | Interrupt save simulation | Original remains valid or new version commits atomically. | NOT RUN
PERSIST-002 | PERSIST | Autosave recovery | Crash after unsaved edits | Recovery offers the latest consistent snapshot. | NOT RUN
PERSIST-003 | PERSIST | Schema migration | Open older fixture | Migration is deterministic and creates backup. | NOT RUN
PERSIST-004 | PERSIST | Serialization round trip | Save/export/import | Canonical fields round-trip exactly. | NOT RUN
PERSIST-005 | PERSIST | Undo depth | Execute 120 edits | At least 100 operations remain undoable. | NOT RUN
PERSIST-006 | PERSIST | View vs data undo | Resize view then edit schedule | Undo stacks do not confuse view geometry with domain edits. | NOT RUN
REP-001 | REP | Saved layout | Save and restore layout | Columns, widths, action columns, geometry and toggles restore. | NOT RUN
REP-002 | REP | Filter AST | Create compound temporal filter | Correct bars/rows match with hierarchy semantics. | NOT RUN
REP-003 | REP | Highlight mode | Apply filter in highlight mode | Context remains and matches are emphasized. | NOT RUN
REP-004 | REP | Multi-key sort | Sort within parent by priority/date | Hierarchy remains valid. | NOT RUN
REP-005 | REP | Timeline range | Save and apply custom range | Visible period changes without schedule mutation. | NOT RUN
REP-006 | REP | Report state | Save full report view | All approved view and print properties restore. | NOT RUN
REP-007 | REP | FastStep | Run multi-command workflow | Commands execute as one recoverable transaction. | NOT RUN
REP-008 | REP | Summary graph | Aggregate count/work/cost by period | Buckets and operations match source data. | NOT RUN
REP-009 | REP | Print preview | Paginate wide Gantt | Headers, footers, legends and page breaks are correct. | NOT RUN
REP-010 | REP | Visual objects | Move, layer and print text/picture/legend | Objects preserve z-order and inclusion settings. | NOT RUN
IO-001 | IO | CSV round trip | Export/import supported table fields | Supported values preserve; losses appear in report. | NOT RUN
IO-002 | IO | XLSX round trip | Export/import hierarchy and dates | Supported hierarchy/data preserve. | NOT RUN
IO-003 | IO | Project XML round trip | Import/export test fixture | Supported tasks, links, resources and calendars preserve. | NOT RUN
IO-004 | IO | ICS round trip | Export/import calendar events | Supported dates and labels preserve. | NOT RUN
IO-005 | IO | PDF export | Export approved report | Output is legible and matches preview. | NOT RUN
IO-006 | IO | Clipboard PNG | Copy visible schedule to PowerPoint/Word | High-resolution image pastes correctly. | NOT RUN
IO-007 | IO | Clipboard vector | Copy SVG/EMF where supported | Vector output remains sharp or reports platform limitation. | NOT RUN
IO-008 | IO | Malformed import | Import invalid file | No project corruption; actionable error and report. | NOT RUN
PERF-001 | PERF | 10k row scroll | Open 10k-row fixture and scroll | Meets published frame-time threshold. | NOT RUN
PERF-002 | PERF | 15k bar zoom | Zoom/pan large timeline | No full-DOM rendering and interaction remains responsive. | NOT RUN
PERF-003 | PERF | 25k dependency move | Move controlling predecessor | Affected-subgraph result matches full solver. | NOT RUN
PERF-004 | PERF | 2k resource aggregation | Open Resource View | Aggregation meets published latency threshold. | NOT RUN
PERF-005 | PERF | 50k assignment load | Open and filter fixture | Memory and latency remain inside published budget. | NOT RUN
PERF-006 | PERF | Cancellation | Cancel long import/refresh | Operation rolls back safely. | NOT RUN
PERF-007 | PERF | Background progress | Run long operation | UI remains responsive and progress is truthful. | NOT RUN

## Checkpoint Log
Checkpoint ID | Date | Phase | Gate | Commit SHA | Implementation Result | Validation Result | User Decision | Evidence Path | Known Gaps | Next Permitted Step
USER-APPROVALS-2026-09-02 | 2026-09-02 | P01 | G-ARCH-01 + UI-00 | 4a773b4093f9db825a0651de4f436458030bad7d | No product implementation | G-HANDOFF-00 pending | APPROVED | governance/approvals/ | Independent handoff validation not yet issued | Run G-HANDOFF-00; on PASS, execute P02 and stop at UI-01

## Approval Records
Gate | Decision | Date | Authority | Reviewed Commit | Conditions | Record Path | Exact User Response | Effective Next Step
G-ARCH-01 | APPROVED | 2026-09-02 | User | 4a773b4093f9db825a0651de4f436458030bad7d | None | governance/approvals/G-ARCH-01_2026-09-02.md | APPROVE G-ARCH-01 APPROVE UI-00 both are approved | Preserve approved architecture; P02 after G-HANDOFF-00 PASS
UI-00 | APPROVED | 2026-09-02 | User | 4a773b4093f9db825a0651de4f436458030bad7d | None | governance/approvals/UI-00_2026-09-02.md | APPROVE G-ARCH-01 APPROVE UI-00 both are approved | Build P02 shell after G-HANDOFF-00 PASS; stop at UI-01